## Weekly Task Plan
EET 4950 – Weekly Task Plan · Safe Dip · Josué Bouchard, Adriano Mena Duque de Estrada · Fall 2026
Every Sunday, set Status (Done, Partial or Slipped) and fill Actual work and notes for the past week. Move slipped tasks to a later week and note it; do not delete the original row.
Owner = who leads the task; With = who helps. Both = a joint event.
Week | Week starting | Milestone | Task | Owner | With | Status | Actual work and notes
6 | 2026-09-28 |  | Rewrite report software section + 4 flowcharts | Josué |  | Done | Section and flowcharts match the firmware
6 | 2026-09-28 |  | Modbus map of cycle status and parameters | Josué |  | Partial | On a branch; not yet tested on the board
6 | 2026-09-28 |  | Fault reporting: latched e-stop, op. state | Josué |  | Partial | On a branch; bench test moved to Week 7
6 | 2026-09-28 |  | Limit-switch inputs and homing operation | Josué |  | Partial | On a branch; switches not yet mounted
6 | 2026-09-28 |  | Document power rails and open-drain wiring | Josué |  | Partial | In wiring.md; E5V supply
6 | 2026-09-28 |  | Website: flowcharts, nav fix, Week 5 log | Josué |  | Done | Posted on the team website
6 | 2026-09-28 |  | CAD: bearing block to plate connections | Adriano |  |  | (Adriano to complete)
6 | 2026-10-12 |  | Fabricate mounting plate and 3D-printed carriage parts; mount bearing blocks on rails | Adriano
7 | 2026-10-05 | Checkpoint 1 – Design Freeze due Sun Oct 11 | Freeze the X-carriage and Y-axis leadscrew CAD; release part drawings and cut list | Adriano
7 | 2026-10-05 |  | Update block diagrams: 24 V supply, open-drain outputs (no buffer), limit switches, E5V | Josué
7 | 2026-10-05 |  | Draw KiCad schematic sheets for power, processing, movement, effector, e-stop and sensing | Josué |  | Partial
7 | 2026-10-05 |  | Test Modbus registers on the board with madbus-cli | Josué
7 | 2026-10-05 |  | Bench-test electromagnet driver: IRLZ44N at 3.3 V gate, flyback diode, coil current | Josué | Adriano
7 | 2026-10-05 |  | Write and submit Checkpoint 1 (Design Freeze) report | Josué | Adriano
7 | 2026-10-05 |  | Add the Weekly Task Plan to the website under the Project Timeline | Josué
8 | 2026-10-12 |  | Install X-axis motor mount and GT2 belt drive on the frame | Adriano
8 | 2026-10-12 |  | Mount X-axis limit switch; wire X driver, motor and switch to the Nucleo | Josué
8 | 2026-10-12 |  | Calibrate X-axis steps/mm; test homing and ±1 cm positioning (R-02) | Adriano | Josué
8 | 2026-10-12 |  | Decide the workpiece-detection sensor (time-of-flight, ultrasonic, or IR presence) and where it mounts at the input station | Josué | Adriano
8 | 2026-10-12 |  | Integrate the chosen sensor and a wait-for-part operation (enable I2C if time-of-flight) | Josué
9 | 2026-10-19 | Checkpoint 2 – Mid-Build and Viability due Sun Oct 25 | Install Y-axis leadscrew assembly, coupler and magnet holder | Adriano
9 | 2026-10-19 |  | Mount Y-axis limit switch; wire Y driver, motor and switch | Josué
9 | 2026-10-19 |  | Wire electromagnet driver to the Nucleo; test engage/release from firmware | Josué
9 | 2026-10-19 |  | Calibrate Y-axis steps/mm; test immersion depth ±1 cm (R-04) | Adriano | Josué
9 | 2026-10-19 |  | Run first two-axis cycle without a part: home, pick, dip, deposit, release | Josué | Adriano
9 | 2026-10-19 |  | Record viability video; write and submit Checkpoint 2 report | Josué | Adriano
10 | 2026-10-26 | W deadline Fri Oct 30 | Wire NC e-stop into the 24 V driver supply and to the e-stop input | Adriano
10 | 2026-10-26 |  | Verify e-stop cuts driver power and restart needs a start press (R-07, R-08) | Adriano | Josué
10 | 2026-10-26 |  | Add limit-switch boundary fault: stop and latch if a switch trips away from 0 | Josué
10 | 2026-10-26 |  | Run cycles with a part: retention and dwell time ±1 s (R-03, R-05) | Adriano | Josué
10 | 2026-10-26 |  | Install fuse holder; tidy and label wiring | Adriano
11 | 2026-11-02 |  | Run full unattended cycle with part detection (R-01, R-06) | Josué | Adriano
11 | 2026-11-02 |  | Verify state and faults are reported over Modbus during a cycle (R-09) | Josué
11 | 2026-11-02 |  | Tune speed and acceleration for cycle time | Josué
11 | 2026-11-02 |  | Start report draft: as-built hardware and software chapters | Josué | Adriano
12 | 2026-11-09 | Report draft due Fri Nov 13 | Run 10 consecutive cycles; record cycle time, depth and dwell (R-10) | Josué | Adriano
12 | 2026-11-09 |  | Run full cycle with a 1 lb payload (R-11) | Adriano | Josué
12 | 2026-11-09 |  | Write test results chapter; publish Final Testing & Results page | Josué
12 | 2026-11-09 |  | Complete and submit report draft (Fri Nov 13) | Josué | Adriano
13 | 2026-11-16 | Final report due Fri Nov 20 | Fix issues found in testing; retest any failed requirement | Josué | Adriano
13 | 2026-11-16 |  | Update budget and power budget with as-built parts and measured currents | Adriano
13 | 2026-11-16 |  | Address draft feedback; submit final report (Fri Nov 20) | Josué | Adriano
14 | 2026-11-23 | Thanksgiving week | Draft presentation slides | Adriano | Josué
14 | 2026-11-23 |  | Record final demo video | Josué | Adriano
14 | 2026-11-23 |  | Website: final timeline, final report and test results pages | Josué
15 | 2026-11-30 | Presentation Fri Dec 4 | Rehearse presentation; prepare demo setup and transport checklist | Adriano | Josué
15 | 2026-11-30 |  | Present the project (Fri Dec 4) | Both
15 | 2026-11-30 |  | Upload final presentation and report to the website | Josué